## Sheet1
Burndown Chart
Industry Burndown
| Hours per week |  | Remaining hours
Week | Planned | Actual | Planned Hours | Actual Hours
2020-08-24 | 0 | 0 | 288 | 288
2020-08-31 | 24 | 14 | 264 | 274
2020-09-07 | 24 | 24 | 240 | 250
2020-09-14 | 24 | 24 | 216 | 226
2020-09-21 | 24 | 21 | 192 | 205
2020-09-28 | 24 | 25 | 168 | 180
2020-10-05 | 24 | 29 | 144 | 151
2020-10-12 | 24 | 24 | 120 | 127
2020-10-19 | 24 | 29.5 | 96 | 97.5
2020-10-26 | 24 | 0 | 72 | 97.5
2020-11-02 | 24 | 0 | 48 | 97.5
2020-11-09 | 24 | 0 | 24 | 97.5
2020-11-16 | 24 | 0 | 0 | 97.5
2020-11-23 | 0 | 0 | 0 | 97.5
| Total Industry Hours: | 190.5
Academic Burndown
| Hours per week |  | Remaining Hours
Week | Planned | Actual | Planned Hours | Actual Hours
2020-08-24 |  |  | 144 | 144
2020-08-31 | 11 | 11 | 133 | 133
2020-09-07 | 11 | 11 | 122 | 122
2020-09-14 | 11 | 7 | 111 | 115
2020-09-21 | 11 | 11 | 100 | 104
2020-09-28 | 12 | 5 | 88 | 99
2020-10-05 | 11 | 13 | 77 | 86
2020-10-12 | 11 | 21 | 66 | 65
2020-10-19 | 11 | 9 | 55 | 56
2020-10-26 | 11 | 0 | 44 | 56
2020-11-02 | 11 | 0 | 33 | 56
2020-11-09 | 11 | 0 | 22 | 56
2020-11-16 | 11 | 0 | 11 | 56
2020-11-23 | 11 | 0 | 0 | 56
| Total Academic Hours: | 88
| Total Hours: | 278.5
Weekly Meetings (Hours) | 18

## Sheet3
2020 Calendar
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Sat | Sun | Week
July | 20
| 27 | Start of Semester Two | [6 empty] | 1
August | 3 | [7 empty] | 2
| 10 | [7 empty] | 3
| 17 | [7 empty] | 4
| 24 | [7 empty] | 5 | 1
| 31 | [7 empty] | 6 | 2
September | 7 | [7 empty] | 7 | 3
| 14 |  |  |  |  | Spring Graduation |  |  | 8 | 4
| 21 | [7 empty] | 9 | 5
| 28 | Sth Canterbury Ann. | [6 empty] | 10 | HALF WAY REPORT
October | 5 | [7 empty] | 11 | HALF WAY REPORT
| 12 | [7 empty] | 12 | 8
| 19 | [7 empty] | 13 | 9
| 26 | L | [6 empty] | 14 | 10
November | 2 | [7 empty] | 15 | 11
| 9 |  |  |  |  | Canterbury Ann. |  |  | 16 | 12
| 16 | Study Week | [6 empty] | 17
| 23 | Exam Week | [7 empty] | Panel presentation
| 30 | Exam Week |  |  |  | DUE DAY |  |  |  | Panel presentation
December | 7 |  | Emerge Event | Examiners Meeting
14
| 21 |  |  | Ara closes 3pm |  | C | B |  | 52